## BO 3 - WBS step 1 the chart
Here is the example from our Lesson
Sub Assemblies |  | Blue Collar Activities |  |  |  | White Collar Activities
Item | Quantity | Part Number | Work Process Description | Name | Material | Purchase | Create in Onshape | Design Thinking | Project Manage
1 | 1 | MTRP-001 | cut, form, strip | wood base | Balsa | x | x | x | x
2 | 1 | MTRP-002 | cut, form | guillotine wire | Copper | x | x | x | x
3 | 1 | MTRP-003 | wind from reel, bend | spring load | Steel 1020 | x | x | x | x
4 | 3 | MTRP-004 | cut, form | spring staple bearing | Copper | x | x | x | x
5 | 1 | MTRP-005 | cut, punch, form, bend | trigger | Copper | x | x | x | x
6 | 1 | MTRP-006 | cut, form | trigger staple bearing | Copper | x | x | x | x
7 | 1 | MTRP-007 | cut, form | trip wire | Copper | x | x | x | x
And Here is a blank version of the table that you can apply as a first step in creating work packages for your Winter Project. Expand the number of lines if necessary.
Sub Assemblies |  | Blue Collar Activities |  |  |  | White Collar Activities
Item | Quantity | Part Number | Work Process Description | Name | Material | Purchase | Create in Onshape | Design Thinking | Project Manage
You can just
invent these.
In this 2nd and final step, you will transfer what you have created in your table above onto sticky notes in Miro that you will arrange under logical headings of your choice to group the work.
Step 1 to make your WBS - Here in Excel
Step 2 to make your WBS - On your Miro board

## BO 5 - The Timeline
Here is the example from your class Workshop Lesson
And here is a template you can apply to make a timeline for your winter project
2022
ID | Taxonomy | Description | Responsibility | Completion | Empathize and Reframe |  |  | Reframe and Ideate |  | Prototype and Feedback | [5 empty] | Hand-over/close | Debrief
[5 empty] | January |  |  |  | February |  |  |  | March |  |  |  | April
[5 empty] | Week 11 | 12 | 13 | 14 | 15 | 16 | Reading Week | 18 | 19 | 20 | 21 | 22 | Final Week | / | / | Legend
1 | A-1 | Initial Empathize | Everyone | ✔️ | [16 empty] | Report/CAD Drawing
2 | A-2 | Needs Statement | Everyone | ✔️ | [16 empty] | Materials
3 | A-3 | Project Plan draft | Everyone | ✔️ | [16 empty] | Roof
4 | A-4 | Second Client meeting | Everyone | ✔️ | [16 empty] | Interior
5 | A-5 | Floor Plan | Samuel | ✔️ | [16 empty] | Hide Structure
6 | A-6 | 1st CAD Design | Elijah | ✔️ | [16 empty] | Fence and Pathway
7 | A-7 | Interior Design | Jason | *
8 | A-8 | Doorway | Nikhil | *
9 | A-9 | Windows | Melissa | * | [15 empty] | Completion Legend
10 | A-10 | Benches | Russell | * | [15 empty] | ✔️ | Completed on Time
11 | A-11 | Emergency Equipment | Jason | * | [15 empty] | ✔️ | Completed Late
12 | A-12 | Walls | Nikhil | * | [15 empty] | * | Still in Progress
13 | A-13 | Foundation | Samuel | * | [15 empty] | - | Not Started
14 | A-14 | General Structure/Exterior Design | Russell | ✔️
15 | A-15 | Accessibility | Elijah | ✔️
16 | A-16 | Purchase materials | Everyone | *
17 | A-17 | Have materials ready for studio | Everyone | *
18 | A-18 | Blending in | Melissa | *
19 | A-19 | Space for birds in roof | Samuel | *
20 | A-20 | Weather proof roof | Elijah | *
21 | A-21 | Pathway to hide | Nikhil | *
22 | A-22 | Fence | Melissa | *
23 | A-23 | Signs | Jason | *
24 | A-24 | Build Presentation | Everyone | *
25 | A-25 | Final CAD | Everyone | -
26 | A-26 | Final Prototype Completion | Everyone | -
27 | A-27 | Hand-over & presentation | Everyone | -
28 | A-28 | Debrief | Everyone | -
You can just
invent these.

## BO - 6 The Risk Analysis
Here is the example from your class Workshop Lesson
And here is a template you can apply to make a timeline for your winter project
Item | Risk Description | Likelihood | Severity | Detectability | RPN# | Mitigation Strategy | Contingency
|  | 2022-01-10 | 2022-01-10 | 2022-01-10 | <100 good | (Accept, Avoid, Reduce, Transfer, Share, Education) | Strategic Response
1 | Wooden structure rots | 3 | 6 | 5 | 90 | Reduce: Use rot resistant wood and avoid direct ground contact with wood | Use environmentally safe treated wood, limit ground contact
2 | Disturbs wildlife | 3 | 4 | 7 | 84 | Avoid: Build hide which blends into landscape, has enclosed pathway. | Build a fence around the pathway to hide people waking into the hide
3 | Design gets flooded | 6 | 6 | 2 | 72 | Accept: Build with flood in mind, raised structure. | Build the hide on higher ground, stronger foundation
4 | People litter in the hide | 7 | 3 | 2 | 42 | Education: place no littering signs outside and inside the hide | Install garbage cans beside the entrance and inside the hide
5 | Materials overbudget | 4 | 5 | 2 | 40 | Avoid: Plan contruction with potential budget in mind | Do not use expensive materials that will use up the budget ineffieciently
6 | People are noisy while approaching | 9 | 2 | 2 | 36 | Education: Place signs telling people to be quiet leading up to the hide | A sound wall beside the hide
7 | Benches get stolen | 2 | 2 | 1 | 4 | Reduce: Fasten bench to wall with chain or secure to ground | Have a chain connected to the bench so it can move, but not be removed